## Contents
GINR Activity: Dec 01, 2018 to Dec 31, 2018
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GINR phase and fuel type
Project Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Project Cancellation Update | A table listing the projects cancelled for the month
Project Details | A table that lists project details; only includes projects for which a Full Interconnection Study has been requested
GINR Trends | Charts and tables that show historical and projected interconnection study trends.
Time of Report Run: Jan 1, 2019 9:16:00 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online GINR system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
http://www.ercot.com/services/rq/re/reg/Resource%20Interconnection%20Handbook.pdf

## Acronyms
Acronyms
GINR = Generation Interconnection or Change Request
COD: Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR: Capacity, Demand and Reserves Report
SFS: Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA: Quarterly Stability Assessment
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage

## Summary
Summary |  |  | Major GINR Milestone Status by Fuel/Technology Type, MW
Currently tracking 465 generation interconnection or change requests as of Dec 31, 2018 |  |  | Includes only those projects for which a Security Screening Study (SS) has been requested.
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Completed | SS Completed | TOTAL
Includes only those projects for which a Security Screening Study (SS) is underway |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Started | FIS Completed
[5 empty] | No IA | No IA | No IA | No IA | No IA | IA | IA
Status of SS, FIS, and IA | Project Count | % of Total | Gas | Combined-Cycle |  |  |  | 1502.5 |  | 1485.8 | 12 | 3000.3
SS Started, FIS Not Started, No IA | 31 | 0.066667 | Gas | Combustion Turbine | 450 | 968 | 1350 | 1763.3 | 100 | 881.8 | 318 | 5831.1
SS Started, FIS Started, No IA | 8 | 0.017204 | Gas | Internal Combustion Engine
SS Completed, FIS Not Started, No IA | 67 | 0.14409 | Gas | Compressed Air Energy Storage | 328 | [6 empty] | 328
SS Completed, FIS Started, No IA | 229 | 0.49247 | Gas | Steam Turbine |  |  | 90 |  |  |  |  | 90
SS Completed, FIS Completed, No IA | 27 | 0.058065 | Gas | Total gas | 778 | 968 | 1440 | 3265.8 | 100 | 2367.6 | 330 | 9249.4
SS Completed, FIS Started, IA | 48 | 0.10323 | Coal
SS Completed, FIS Completed, IA | 55 | 0.11828 | Wind |  | 346.4 |  | 6232.8 | 18217.2 | 519 | 6451.51 | 7829.54 | 39596.45
Total Interconnection Requests | 465 |  | Solar |  | 6233.1 | 947.43 | 5710.73 | 22897.27 | 606.9 | 3419.66 | 917.4 | 40732.49
Cancelled Studies (since last month) | 9 |  | Biomass
| Capacity, MW |  | Other | Battery | 116 | 242.22 | 430.5 | 1554.1 |  |  |  | 2342.82
Total Capacity Under Study | 91921.16 |  | Other*
Interconnection Agreements Executed | 21315.71 |  | TOTAL |  | 7473.5 | 2157.65 | 13814.03 | 45934.37 | 1225.9 | 12238.77 | 9076.94 | 91921.16
Cancelled (since last month) | 1981 |  | * Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, and other miscellaneous fuels reported by developers.

## Project Commissioning Update
Commissioning Approvals During December 2018
Commissioning Category | INR | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 15INR0035 | Stella 1 Wind | Wind | Kenedy | 2018-12-19 | 201
Commercial Operation Approved by ERCOT* | 16INR0023b | Lamesa Solar B (Phase II) IVORY | Solar | Dawson | 2018-12-19 | 50
Commercial Operation Approved by ERCOT* | 16INR0115 | Waymark Solar | Solar | Pecos | 2018-12-20 | 182
Synchronization Approved by ERCOT | 11INR0054 | Midway Wind | Wind | San Patricio | 2018-12-04 | 162.9
Synchronization Approved by ERCOT | 18INR0078 | Bobcat Bluff repower | Wind | Archer | 2018-12-20 | 12
Synchronization Approved by ERCOT | 18INR0079 | Woodward I repower | Wind | Pecos | 2018-12-18 | 0
Synchronization Approved by ERCOT | 18INR0080 | Woodward 2 repower | Wind | Pecos | 2018-12-19 | 0
Synchronization Approval Revoked by ERCOT | 17INR0022 | MIRAGE | Gas | Harris | 2018-12-19 | 11
Energization Approved by ERCOT | 18INR0070 | Blue Summit II | Wind | Wilbarger | 2018-12-18 | 102
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Project Cancellation Update
Projects Cancelled by the Developer during December 2018*
INR | Project Name | Fuel | County | Cancel Date | MW **
18INR0022 | Winkler Solar | Solar | Winkler | 2018-12-07 10:32 | 150
18INR0057 | Green Valley Wind | Wind | Val Verde | 2018-12-20 15:42 | 500
19INR0139 | Craver Ranch | Solar | Denton | 2018-12-20 09:51 | 100
* Includes only those projects cancelled after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Project Details
GINR Project Details
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GINR system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not obtained or reported to ERCOT yet.
Project Attributes | [10 empty] | Changes from Last Report | GINR Project Milestone Dates
INR | Project Name | GINR Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | IA Signed | Financial Security | Air Permit | GHG Permit | Water Availability | Meets Planning Guide Section 6.9(1) | Meets Planning Guide Section 6.9 | Meets Planning Guide | Construction Start | Construction End | Approved for Energization | Approved for Synchronization
[11 empty] | Change indicators: Proj Name, MW | [5 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Size , COD, SFS/NtP, FIS Request | [5 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[21 empty] | Models | Models
08INR0019b | Grandview 5 W | SS Completed, FIS Started, No IA | Eon | 79005 Railhead 345kV | Gray | PANHANDLE | 2020-12-15 | WIN | WT | 249 |  | 2006-07-21 | 2006-10-02 | 2006-07-21 |  |  | No | Not Required | Not Required | Not Required
11INR0054 | Midway Wind | SS Completed, FIS Completed, IA | Apex Clean | 8961 Whitepoint 138kV | San Patricio | COASTAL | 2018-12-15 | WIN | WT | 162.9 |  | 2009-02-26 | 2009-05-28 | 2009-11-30 | 2018-04-19 | 2017-11-05 | Yes | Not Required | Not Required | Not Required | 2018-04-24 | 2018-09-28 | 2018-04-24 |  |  | 2018-10-23 | 2018-12-04
11INR0062 | Shaffer | SS Completed, FIS Completed, IA | NRG | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2019-03-08 | WIN | WT | 226 | COD | 2009-04-23 | 2009-06-16 | 2009-07-21 | 2018-06-13 | 2018-04-13 | Yes | Not Required | Not Required | Not Required | 2018-04-18 | 2018-09-28 | 2018-04-18
12INR0002a | Silver Canyon Wind A | SS Completed, FIS Completed, IA | EDP Renewables | 79503 Tule Canyon 345kV | Briscoe | PANHANDLE | 2020-10-31 | WIN | WT | 200 |  | 2007-01-03 | 2007-01-26 | 2007-07-31 | 2018-08-30 | 2016-06-22 | No | Not Required | Not Required | Not Required
12INR0029 | Comanche Run Wind | SS Completed, FIS Started, IA | Avangrid | 79501 Ogallala 345kV | Swisher | PANHANDLE | 2019-12-31 | WIN | WT | 500 |  | 2009-03-02 | 2009-05-28 | 2009-07-01 |  | 2013-07-24 | No | Not Required | Not Required | Not Required
12INR0055 | S_Hills Wind | SS Completed, FIS Completed, IA | SEYMOUR HILLS WIND PROJECT, LLC | 33728 Mabelle 69kV | Baylor | WEST | 2019-04-01 | WIN | WT | 30.24 |  | 2010-09-28 | 2010-12-20 | 2016-08-17 | 2018-06-19 | 2017-12-04 | Yes | Not Required | Not Required | Not Required | 2018-10-04 |  | 2018-10-04
12INR0059b | HOVEY (Barilla Solar 1B) | SS Completed, FIS Completed, IA | First Solar | 60385 Solstice 138kV | Pecos | WEST | 2019-02-28 | SOL | PV | 7.4 |  | 2010-12-01 | 2011-02-25 | 2011-08-09 | 2014-01-16 | 2013-12-26 | Yes | Not Required | Not Required | Not Required
12INR0060 | Wilson Ranch | SS Completed, FIS Completed, IA | ENGIE | 76003 Big Hill 345kV | Schleicher | WEST | 2019-01-24 | WIN | WT | 199.5 |  | 2010-12-03 | 2014-03-21 | 2011-06-06 | 2018-05-31 | 2018-05-21 | Yes | Not Required | Not Required | Not Required | 2018-05-21 | 2018-09-28 | 2018-05-21 |  |  | 2018-10-11 | 2018-11-29
13INR0010a | Mariah Del Este | SS Completed, FIS Started, IA | Mariah Acquisition | 141765 Mariah 345kV | Parmer | PANHANDLE | 2019-03-29 | WIN | WT | 152.5 | COD | 2009-06-29 | 2009-09-25 | 2010-03-26 |  | 2013-01-31 | Yes | Not Required | Not Required | Not Required | 2018-04-30 | 2018-04-30 | 2018-04-30
13INR0010def | Scandia Wind DEF | SS Completed, FIS Completed, IA | Scandia Wind LLC | 141765 Mariah 345kV | Parmer | PANHANDLE | 2020-04-01 | WIN | WT | 600.3 |  | 2009-06-29 | 2009-09-25 | 2010-03-26 | 2017-08-03 | 2014-04-25 | No | Not Required | Not Required | Not Required
13INR0025 | Northdraw Wind | SS Completed, FIS Started, IA | National Renewable Solutions | 79504 AJ Swope 345kV | Randall | PANHANDLE | 2020-08-01 | WIN | WT | 150 | COD | 2010-06-15 | 2010-09-02 | 2011-03-01 |  | 2018-04-25 | No | Not Required | Not Required | Not Required
13INR0026 | Canadian Breaks Wind | SS Completed, FIS Completed, IA | Macquarie Cap | Tap 345kV 79502 Windmill - 79504 AJ Swope | Oldham | PANHANDLE | 2019-09-13 | WIN | WT | 210 |  | 2010-07-06 | 2010-10-04 | 2011-04-01 | 2017-03-16 | 2016-05-20 | Yes | Not Required | Not Required | Not Required | 2018-09-04 | 2018-10-30 | 2018-09-04
13INR0038 | Wildrose Wind | SS Completed, FIS Started, IA | S Power | 79501 Ogallala 345kV | Swisher | PANHANDLE | 2020-12-30 | WIN | WT | 302.5 |  | 2011-05-01 | 2011-05-26 | 2011-11-02 |  | 2015-09-06 | Yes | Not Required | Not Required | Not Required | 2017-05-04 |  | 2017-05-04
14INR0009 | WKN Amadeus Wind | SS Completed, FIS Started, IA | WKN | tap 345kV 11305 Dermott - 60704 Kirchhof | Fisher | WEST | 2020-05-15 | WIN | WT | 245.9 | COD | 2011-01-24 | 2011-03-18 | 2011-09-12 |  | 2018-03-15 | No | Not Required | Not Required | Not Required
14INR0030c | Panhandle Wind 3 | SS Completed, FIS Started, IA | Pattern Energy | 79005 Railhead 345kV | Carson | PANHANDLE | 2020-12-01 | WIN | WT | 248 |  | 2012-07-03 | 2012-08-17 | 2014-03-26 |  | 2014-08-25 | Yes | Not Required | Not Required | Not Required | 1899-12-31 |  | 1899-12-31
14INR0033 | Goodnight Wind | SS Completed, FIS Completed, IA | FGE Power | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2019-08-11 | WIN | WT | 496.8 |  | 2012-07-24 | 2012-09-19 | 2013-03-04 | 2017-09-25 | 2018-03-07 | No | Not Required | Not Required | Not Required
14INR0044 | West of Pecos Solar | SS Completed, FIS Started, IA | Eon | 1094 Mason 138kV | Reeves | WEST | 2019-12-15 | SOL | PV | 100 |  | 2013-01-21 | 2013-02-19 | 2013-06-12 |  | 2017-02-27 | Yes | Not Required | Not Required | Not Required | 2017-05-04 |  | 2017-05-04
14INR0045 | Torrecillas Wind | SS Completed, FIS Completed, IA | Nextera | 161252, 161301 Torrecillas 34.5kV | Webb | SOUTH | 2019-03-01 | WIN | WT | 300.5 | COD SFS/NtP | 2013-01-30 | 2013-03-14 | 2013-01-30 | 2018-05-14 | 2018-04-12 | Yes | Not Required | Not Required | Not Required | 2018-04-26 | 2018-04-26 | 2018-04-26 |  |  | 2018-11-09
16INR0003 | LEVEE (Freeport LNG) | SS Completed, FIS Completed, IA | Freeport LNG | 43336 Oyster Cr 138kV | Brazoria | COASTAL | 2019-08-01 | GAS | GT | 11 |  | 2011-12-15 | 2012-02-15 | 2012-01-04 | 2018-01-22 | 2014-01-13 | Yes | 2014-07-16 | Not Required |  | 2018-10-09 | 2018-10-09 | 2018-10-09
16INR0010 | FGE Texas 1 Gas | SS Completed, FIS Started, IA | FGE Power | Tap 345kV 1030 Morgan - 1025 Falcon | Mitchell | WEST | 2021-04-30 | GAS | CC | 742.9 |  | 2013-04-24 | 2013-05-29 | 2013-05-14 |  | 2016-08-31 | No | 2016-12-16 | 2016-12-12 | 2014-01-29
16INR0045 | Halyard Henderson | SS Completed, FIS Started, IA | Halyard Energy | tap 345kV 3109 Stryker - 3123 Trinidad | Henderson | NORTH | 2021-05-01 | GAS | GT | 484 |  | 2014-03-20 | 2014-04-15 | 2014-07-21 |  | 2016-04-01 | No | 2015-12-08 | Not Required | 2016-01-05
16INR0054 | NA | SS Completed, FIS Completed, IA | NASA | 42970 Nasa 138kV | Harris | HOUSTON | 2018-09-01 | GAS | CC | 12 |  | 2015-03-10 | 2015-04-01 | 2015-03-10 | 2016-01-26 | 2016-10-27 | Yes | Not Required | Not Required |  | 2016-11-10 | 2018-09-28 | 2016-11-10 |  |  |  | 2017-11-27
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, No IA | Infinity Renewables | 76005 Schneeman Draw 345kV | Crockett | WEST | 2019-12-01 | WIN | WT | 400 |  | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2018-12-11 |  | No | Not Required | Not Required | Not Required
19INR0176 | Roughneck Storage | SS Completed, FIS Started, No IA | Glidepath | 43390 W Columbia 69kV | Brazoria | COASTAL | 2020-04-01 | OTH | BA | 52.25 | Proj Name MW Size | 2018-05-09 | 2018-07-13 |  |  |  | No | Not Required | Not Required | Not Required
20INR0206 | PES1 | SS Completed, FIS Started, No IA | ProEnergy Services LLC | 47150 H O Clarke 138kV | Harrison | EAST-SPP | 2020-06-01 | GAS | GT | 484 |  | 2018-10-23 | 2018-11-16 | 2018-10-11 |  |  | No | Not Required | Not Required
20INR0219 | Eunice Solar | SS Started, FIS Started, No IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2020-12-31 | SOL | PV | 403.8 | FIS Request | 2018-12-06 |  | 2018-11-30 |  |  | No |  |  | Not Required

## GINR Trends
GINR Trends
Reflects all projects for which a Security Screening Study has been requested.
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Active Projects | Project Count | [5 empty] | Project Capacity (MW)
|  |  |  | GINR milestones | [5 empty] | Fuel Type
|  |  |  | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Other
| 2015 | Dec | 255 | 3 | 21 | 131 | 10 | 90 | 15 | 24095 | 8509 | 27686 | 0 | 240 | 0 | 614
| 2016 | Jan | 241 | 4 | 13 | 124 | 10 | 90 | 14 | 24472 | 7713 | 24383 | 0 | 240 | 0 | 614
| 2016 | Feb | 236 | 3 | 12 | 118 | 14 | 89 | 8 | 23508 | 7757 | 23058 | 0 | 240 | 0 | 644
| 2016 | Mar | 236 | 3 | 16 | 112 | 12 | 93 | 5 | 24197 | 7482 | 23158 | 0 | 240 | 0 | 644
| 2016 | Apr | 241 | 8 | 12 | 111 | 11 | 99 | 5 | 24951 | 7762 | 22982 | 0 | 240 | 0 | 644
| 2016 | May | 236 | 4 | 16 | 108 | 8 | 100 | 9 | 25304 | 7414 | 23149 | 0 | 240 | 0 | 644
| 2016 | Jun | 232 | 12 | 14 | 104 | 8 | 94 | 8 | 25215 | 8321 | 22471 | 0 | 240 | 0 | 644
| 2016 | Jul | 231 | 13 | 16 | 98 | 7 | 96 | 7 | 25215 | 8321 | 22304 | 0 | 240 | 0 | 644
| 2016 | Aug | 235 | 17 | 24 | 88 | 6 | 100 | 5 | 25895 | 9538 | 21077 | 0 | 240 | 0 | 694
| 2016 | Sep | 226 | 10 | 22 | 90 | 6 | 98 | 7 | 25254 | 9391 | 19671 | 0 | 240 | 0 | 694
| 2016 | Oct | 250 | 16 | 27 | 93 | 6 | 99 | 2 | 26643 | 12439 | 19771 | 0 | 240 | 0 | 674
| 2016 | Nov | 247 | 18 | 31 | 98 | 3 | 98 | 3 | 26643 | 12439 | 19771 | 0 | 240 | 0 | 674
| 2016 | Dec | 254 | 23 | 33 | 103 | 2 | 96 | 4 | 26732 | 13724 | 18816 | 0 | 240 | 0 | 624
| 2017 | Jan | 257 | 16 | 36 | 105 | 4 | 96 | 2 | 26270 | 14498 | 18816 | 0 | 240 | 0 | 624
| 2017 | Feb | 263 | 8 | 33 | 127 | 2 | 93 | 5 | 26512 | 14958 | 19016 | 0 | 240 | 0 | 30
| 2017 | Mar | 264 | 11 | 27 | 131 | 3 | 92 | 3 | 26593 | 15338 | 16750 | 0 | 240 | 0 | 0

## data_GINR Trends_1
| # Initial Screening study | # Screening Study Complete | # in Full Study | # Completed Full Study | # Signed Interconnect Agreement | MW Capacity
Dec-17 | 7 | 57 | 166 | 19 | 73 | 68320
Jan-18 | 15 | 56 | 169 | 21 | 74 | 66927
Feb-18 | 11 | 46 | 177 | 27 | 73 | 67398
Mar-18 | 14 | 41 | 179 | 27 | 79 | 68477
Apr-18 | 18 | 48 | 172 | 30 | 81 | 71620
May-18 | 33 | 36 | 180 | 34 | 86 | 75207
Jun-18 | 32 | 42 | 190 | 27 | 88 | 77020
Jul-18 | 34 | 60 | 197 | 25 | 88 | 80416
Aug-18 | 26 | 57 | 220 | 26 | 88 | 83491
Sep-18 | 30 | 67 | 212 | 26 | 91 | 82461.35
Oct-18 | 26 | 60 | 221 | 24 | 98 | 83449.1
Nov-18 | 23 | 59 | 235 | 26 | 100 | 86517.24
Dec-18 | 31 | 67 | 237 | 27 | 103 | 91921.16

## data_GINR Trends_2
| MW Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Other | Total Project Count | Cancelled Project Count
Dec-17 | 13969 | 0 | 0 | 30198 | 24123 | 0 | 30 | 337 | 8
Jan-18 | 12768 | 0 | 0 | 31420 | 22739 | 0 | 0 | 335 | 17
Feb-18 | 12727 | 0 | 0 | 32258 | 22413 | 0 | 0 | 334 | 9
Mar-18 | 12065 | 0 | 0 | 32897 | 23515 | 0 | 0 | 340 | 8
Apr-18 | 13484 | 0 | 0 | 33427 | 24709 | 0 | 0 | 349 | 4
May-18 | 13442 | 0 | 0 | 33799 | 27766 | 0 | 200 | 369 | 13
Jun-18 | 13674 | 0 | 0 | 34376 | 28448 | 0 | 522 | 379 | 6
Jul-18 | 11668 | 0 | 0 | 37708 | 30518 | 0 | 522 | 404 | 6
Aug-18 | 10814 | 0 | 0 | 40851 | 29649 | 0 | 2177 | 417 | 11
Sep-18 | 8589.6 | 0 | 0 | 40327.45 | 31655.3 | 0 | 1889 | 426 | 15
Oct-18 | 9073.6 | 0 | 0 | 40237.59 | 32248.91 | 0 | 1889 | 429 | 4
Nov-18 | 7503.4 | 0 | 0 | 40283.09 | 36682.4 | 0 | 2048.35 | 443 | 7
Dec-18 | 9249.4 | 0 | 0 | 39596.45 | 40732.49 | 0 | 2342.82 | 465 | 9

## data_GINR Trends_3
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2018 |  | 162.9
| 2019 | 664 | 2041.7
| 2020 | 400 | 1769 | 1663.9 | 233.35
| 2021 |  |  | 1050 | 156.8
HOUSTON | 2018 | 12
| 2019 | 11
| 2020 | 1202.6 |  | 540
| 2021 | 552.2 |  | 300
WEST | 2018 |  | 277.4
| 2019 |  | 6462.34 | 3107.3
| 2020 |  | 7534.9 | 9969.64 | 81.26
| 2021 | 742.9 | 2397.5 | 6743.75 | 886.6
| 2022 | 742.9 |  | 600
NORTH | 2019 | 44 | 592.8 | 373
| 2020 | 1134 | 2154.2 | 4419.6 | 346
| 2021 | 1957.5 | 700.2 | 2349.69 | 82
| 2022 | 328 |  | 1050
PANHANDLE | 2019 |  | 2040.7 | 340.8
| 2020 |  | 3917.5 | 1604.6
| 2021 | 81.5 | 653.9 | 150
SOUTH | 2019 | 145 | 3847.8 | 825 | 38
| 2020 | 350 | 4143.61 | 2610.39 | 130.2
| 2021 | 397.8 | 900 | 3034.82 | 388.61