## Contents
GIM Activity: Sep 01, 2026 to Sep 30, 2026
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GIM phase and fuel type
Project Details - Large Gen | A table that list project details for Large Generators as defined in ERCOT Planning Guide Section 5.2.1(3); only include projects for which a Full Interconnection Study has been requested
Project Details - Small Gen | A table that list project details for Small Generators as defined in ERCOT Planning Guide 5.2.1(3); only include projects for which the Resource Registration form has been approved by ERCOT
GIM Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Oct 1, 2026 8:00:45 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online RIOO system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
See the Resource Interconnection Handbook, available on ERCOT’s Resource Integration webpage:
http://www.ercot.com/services/rq/integration

## Acronyms
Acronyms
GIM = Generator Interconnection or Modification request
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types

## Summary
Summary |  |  | Major GIM Milestone Status by Fuel/Technology Type, MW
Currently tracking 1874 generation interconnection or change requests as of Sep 30, 2026 |  |  | Includes only those (1) Large Generator projects for which a Screening Study has been requested, (2) Small Generators for which an interconnection request has been made, and (3) projects that are not Inactive
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Started | SS Started | SS Completed | SS Completed | SS Completed | Small Generator | Small Generator | TOTAL
Includes only those (1) Large Generator projects for which a Screening Study has been requested, |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | Not Model Ready | Model Ready
(2) Small Generators for which an interconnection request has been made and |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA | IA | IA | IA
and (3) projects that are not Inactive
Status of SS, FIS and IA | Project Count | % of Total | Gas | Combined-Cycle |  | 4993.62 | 1708 | 28600.49 | 34.5 |  |  |  | 6860.4 | 1371 | 9.9 | 9.3 | 43587.21
LARGE GENERATORS |  |  | Gas | Combustion Turbine | 173 | 2780.5 | 18 | 13096.22 | 736.5 |  |  |  | 3178.71 | 4227.46 |  |  | 24210.39
SS Started, FIS Not Started, No IA | 8 | 0.0042689 | Gas | Internal Combustion Engine |  | 832.88 |  | 9411.03 |  |  |  |  | 678.11 | 925.38 | 19.98 | 19.89 | 11887.27
SS Started, FIS Started, No IA | 50 | 0.026681 | Gas | Compressed Air Energy Storage
SS Completed, FIS Not Started, No IA | 41 | 0.021878 | Gas | Steam Turbine |  |  |  | 1335 | [5 empty] | 14 |  |  | 1349
SS Completed, FIS Started, No IA | 1009 | 0.53842 | Gas | Fuel Cell
SS Completed, FIS Completed, No IA | 110 | 0.058698 | Gas | Total gas | 173 | 8607 | 1726 | 52442.74 | 771 |  |  |  | 10717.22 | 6537.84 | 29.88 | 29.19 | 81033.87
SS Started, FIS Not Started, IA | 0 | 0 | Coal
SS Started, FIS Started, IA | 0 | 0 | Wind |  | 1351.4 | 2460.03 |  | 25737.83 | 287.02 |  |  | 486.4 | 11157.32 | 8266.02 |  |  | 49746.02
SS Completed, FIS Not Started, IA | 5 | 0.0026681 | Solar |  | 800 | 5075.55 | 4650.92 | 73972.9 | 5995.8 |  |  | 304.94 | 33353.34 | 30928.83 | 30.68 | 9.9 | 155122.86
SS Completed, FIS Started, IA | 268 | 0.14301 | Biomass
SS Completed, FIS Completed, IA | 316 | 0.16862 | Other | Battery | 900 | 1269.82 | 4139.61 | 106027.68 | 11608.45 |  |  | 132.98 | 18170.7 | 19834.3 | 282.49 | 213.58 | 162579.61
SMALL GENERATORS |  |  | Other* |  |  | 1370 | 930 | 2980.15 | [7 empty] | 19.9 | 5300.05
Not Model Ready* | 36 | 0.01921 | TOTAL |  | 3224.4 | 18782.4 | 11446.53 | 261161.3 | 18662.27 |  |  | 924.32 | 73398.58 | 65566.99 | 343.05 | 272.57 | 453782.41
Model Ready* | 31 | 0.016542 | * Other includes petroleum coke (pet coke), hydroelectric, fuel oil, nuclear, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.
Total Interconnection Requests | 1874
Inactive (since last month) | 13

## Project Details - Large Gen
GIM Project Details - Large Generators
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GIM system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
A “1-1-1900” date is used to signify that an actual date for a project milestone is not available. This typically occurs for project data migrated from the legacy GINR database to the RIOO system.
Project Attributes | [10 empty] | Changes from Last Report | GIM Project Milestone Dates
INR | Project Name | GIM Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | McCrae Wind Energy II, LLC | 59903 Bearkat 345kV | Glasscock | WEST | 2026-12-03 | WIN | WT | 162.1 |  |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
16INR0049 | Nazareth Solar | SS Completed, FIS Completed, IA | TX Nazareth Solar, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala C2 | Castro | PANHANDLE | 2027-08-31 | SOL | PV | 203 |  | 2014-07-07 | 2014-06-19 | 2014-07-25 | 2014-07-01 | 2025-07-29 | No | 2026-03-05 | Yes | Not Required | Not Required | Not Required | 2024-03-22
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2027-03-01 | WIN | WT | 201.6 |  | 2014-12-30 | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | No | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
16INR0085 | Priddy Wind | SS Completed, FIS Completed, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2026-12-31 | WIN | WT | 302.4 |  | 2015-03-06 | 2015-01-14 | 2015-02-10 | 2015-03-06 | 2021-04-30 | No | 2020-08-13 | Yes | Not Required | Not Required | Not Required | 2021-03-29 | 2021-04-30 | 2021-04-30 |  |  | 2021-10-13 | 2021-11-19
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, IA | Big Sampson Wind Project, LLC | tap 345kV 76015 Cedar Canyon - 7053 Noelke | Crockett | WEST | 2026-09-01 | WIN | WT | 265.4 |  |  | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2024-10-30 | Yes | 2019-11-08 | Yes | Not Required | Not Required | Not Required | 2024-10-31 | 2024-11-04 | 2024-11-04 |  |  | 2025-06-04 | 2025-06-16
16INR0112 | Loma Pinta Wind | SS Completed, FIS Started, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2026-12-31 | WIN | WT | 197.01 |  |  | 2015-05-18 | 2015-07-02 | 2015-05-18 |  | No | 2017-12-13 | No | Not Required | Not Required | Not Required
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2026-08-28 | WIN | WT | 242.6 |  |  | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | No | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31 |  |  | 2020-08-24 | 2020-11-25
17INR0043 | Vaquero 1 Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | SOUTH | 2027-01-15 | WIN | WT | 400 |  | 2016-04-01 | 2016-04-01 | 2016-05-10 | 2016-04-01 |  |  |  | No | Not Required | Not Required | Not Required
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2027-03-31 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | No | 2019-05-22 | Yes | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-03-16
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2027-03-31 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 | No | 2009-06-26 | No | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-09-10
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2026-06-30 | WIN | WT | 32 |  | 2017-03-09 | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | No | 2006-11-14 | No | Not Required | Not Required | Not Required | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-04
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | TRENT WIND FARM LLC | 1338 Eskota 138kV | Nolan | WEST | 2026-01-01 | WIN | WT | 6.4 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | No | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | DESERT SKY WIND FARM LLC | two LCRA 138kV | Pecos | WEST | 2023-05-16 | WIN | WT | 7.2 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | No | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0009 | Eagle Pines Gas | SS Completed, FIS Started, No IA | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | NORTH | 2028-10-30 | GAS | CC | 1173.5 |  | 2015-03-24 | 2015-03-30 | 2015-06-23 | 2015-04-29 |  |  |  | No | 2017-02-14 | 2015-11-04 |  |  |  |  | 2026-01-30 | 2028-08-14
18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2026-08-31 | WIN | WT | 182.4 |  | 2016-07-22 | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | No | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31 |  |  | 2021-01-08 | 2021-04-23
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, IA | Monte Alto Windpower, LLC | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2028-12-31 | WIN | WT | 199.2 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2022-03-22 | Yes | Not Required | Not Required | Not Required | 2025-02-12
20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2028-04-08 | OTH | BA | 50.14 |  | 2019-04-30 | 2019-01-14 | 2019-03-19 | 2019-04-26 |  |  |  | No | Not Required | Not Required
21INR0012 | Air Products GCA | SS Completed, FIS Completed, IA | Air Products | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | Galveston | HOUSTON | 2025-12-31 | GAS | ST | 14 |  | 2019-03-26 | 2018-06-07 | 2018-08-01 |  | 2023-03-10 |  | 2020-08-07 | Yes | Not Required | Not Required | 2020-03-31 | 2023-03-13 | 2023-03-13 | 2023-03-13 |  |  | 2023-11-07 | 2024-07-10
21INR0220 | Maleza Solar | SS Completed, FIS Not Started, IA | Brush Solar LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2028-12-31 | SOL | PV | 254.94 |  | 2019-03-07 | 2018-12-06 | 2019-01-18 |  |  | No | 2021-01-13 | Yes |  |  | Not Required | 2022-12-08
21INR0527 | Hays Energy Unit 3 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays 345kV | Hays | SOUTH | 2028-07-01 | GAS | GT | 18 | COD | 2021-02-09 | 2020-10-07 | 2020-12-30 | 2021-02-05 |  |  |  | No | 2020-11-05
21INR0532 | Brazos Wind Repower | SS Completed, FIS Completed, No IA | BRAZOS WIND VENTURES, LLC | 1064 Sun 138kV | Scurry | WEST | 2025-11-14 | WIN | WT | 22.4 |  | 2020-12-18 | 2020-12-22 | 2021-03-10 | 2020-11-30 | 2022-04-01 |  |  | Yes | Not Required | Not Required | Not Required | 2022-08-03 | 2022-10-21 | 2023-02-03 |  |  | 2023-04-25 | 2023-07-01
22INR0546 | Enchanted Rock NEWPP | SS Completed, FIS Completed, IA | Generate ER-NG, LLC | 40475 Deusen 138kV | Harris | HOUSTON | 2026-02-28 | GAS | IC | 30 |  | 2022-12-01 | 2021-11-10 | 2022-01-17 | 2022-07-13 | 2024-04-19 | No | 2024-04-30 | Yes | 2024-04-25 | Not Required | 2024-04-30 | 2024-05-01 | 2024-05-01 | 2024-05-01
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  | No |  | No | Not Required | Not Required
26INR0396 | Kodiak AGR1 | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | 38113 TNCOYOTSPG1 | Reeves | WEST | 2029-06-08 | OIL | OT | 132 | COD | 2024-10-03 | 2024-02-27 | 2024-05-28 | 2024-09-10 |  |  |  | No
26INR0515 | Rio Grand Valley Element Fuels Power | SS Completed, FIS Started, No IA | Element H2Gen, LLC | Tap 138kV 59450 Waterport Substation - 5789 Southmost Sub | Cameron | COASTAL | 2028-12-05 | HYD | OT | 79.63 |  | 2025-04-14 | 2024-06-13 | 2024-09-10 | 2025-03-03 |  |  |  | No
27INR0557 | STP Unit2 High Pressure Turbine Upgrade | SS Completed, FIS Started, No IA | Constellation South Texas, LLC | 5915 SO_TEX__345A 345 kV | Matagorda | COASTAL | 2027-04-23 | NUC | ST | 1336.52 |  | 2026-04-28 | 2026-04-30 | 2026-07-24 | 2026-04-29 |  |  |  | No |  |  | 2026-09-10
27INR0570 | Sisters Solar - Phase 2 | SS Started, FIS Started, No IA | Oberon Solar IV, LLC | 10009 McGee 345 kV | Ector | WEST | 2028-09-23 | SOL | PV | 201.51 |  | 2026-07-14 | 2026-07-22 |  | 2026-07-22 |  |  |  | No |  |  | Not Required
27INR0655 | Lynx Energy Storage_Full | SS Started, FIS Started, No IA | Corpus Battery Storage, LLC | PRIMAVERA 138kV Substation | Nueces | COASTAL | 2027-12-01 | MWH | SO | 50 | FIS Request | 2026-08-20 | 2026-08-06 |  | 2026-09-01 |  |  |  | No
30INR0002 | Southeast Oklahoma Pumped Storage | SS Completed, FIS Started, No IA | Apex Energy Solutions, LLC | 1692 Paris Switch 345kV | Lamar | NORTH | 2030-01-01 | WAT | OT | 1232 |  | 2023-03-28 | 2022-08-05 | 2022-11-01 | 2023-03-10 |  |  |  | No

## Project Details - Small Gen
GIM Project Details - Small Generators
NOTES:
Due to Protocol confidentiality provisions, only those Small Generator projects are included for which ERCOT has (1) received written Notice from Interconnecting Entities (IE) that authorize the project
information to be made public, or (2) approved the IE's completed Resource Registration form as indicated by assignment of a “Model Ready Date".
Excludes projects that have a status of Inactive (status = INA).
INR | Project Name | Model Ready Date | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) | Change indicators: Proj Name, MW | IA Signed | Financial Security | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Size, COD, SFS. |  | Required to fund
[11 empty] | Status Change INA-to-PLN |  | Dist. Upgrades
22INR0596 | Grizzly Ridge BESS SLF | 2022-09-01 | Grizzly Ridge Solar LLC | Pottsville Switching Substation (Bus# 178) | Hamilton | NORTH | 2030-07-01 | OTH | BA | 0 |  | 2021-10-18 | Yes | 2023-02-10
23INR0483 | Rio Nogales CT1 Rotor Replacement | 2023-04-12 | CPS Energy | Rio Nogales Substation 5362 RIONOG 345kV | Guadalupe | SOUTH | 2026-08-07 | GAS | CC | 3.1 |  | 2023-01-20 | Yes |  | 2023-04-27
23INR0529 | Torrecillas BESS | 2024-09-05 | Torrecillas Interconnect, LLC | 161257 Torrecillas 345kV Station code: TORR | Webb | SOUTH | 2026-12-31 | OTH | BA | 9.9 |  | 2015-01-30 | Yes | 2025-06-25 | 2025-07-01
23INR0548 | Leakey BESS | 2026-06-03 | Regis Leaky LLC | Station Name (TDSP Station Code): LEAKEY; Load/Load Transformer Name: L_LEAKEY9_1Y; PTI BUS Name: 7426; Voltage in kV (Transmission Level): 69kV Transformers: 3x 4000kVA 800VAC Δ - 24.9kVA Υ 12,000 MVA connected, Running load limited to 9.99 MW | Real | SOUTH | 2026-11-13 | OTH | BA | 9.9 |  | 2023-01-18 | Yes | 2026-07-02 | 2026-07-10
23INR0556 | IEP Orchard BESS | 2024-01-04 | IEP Tejas Verde LLC | Station Name (TDSP Station Code): OR Load/Load Transformer Name :TR1 PTI BUS number: 44541 Voltage in kV (Transmission Level): 138 kV Project Size: 9.99 MW battery energy storage (BESS) system; 50 MWh connecting on CNP 34.5kV Distribution System. | Fort Bend | HOUSTON | 2027-12-31 | OTH | BA | 9.99 | COD | 2023-08-09 | Yes | 2024-11-12 | 2024-12-06
23INR0603 | Damon BESS 2 | 2024-07-03 | PR DAMON, LLC | 9.99 MW 50 MWh battery energy storage project connecting at 12.47kV Damon (DA) substation. Station Name (TDSP Station Code): DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV | Brazoria | COASTAL | 2027-08-21 | OTH | BA | 9.99 |  | 2023-10-06 | Yes
23INR0790 | DAMON BESS3 | 2025-09-04 | BarBar Storage LLC | Station Name: DAMON TSP Station Code: DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV Node (associated w/ load/load XFRM in NMMS): TR2 | Brazoria | COASTAL | 2025-12-01 | OTH | BA | 9.96 |  | 2024-01-30 | Yes | 2025-09-29 | 2026-03-04
24INR0481 | Little York BESS | 2026-02-04 | ESTX-PLD-HOUSTON5, LLC | Station Name (TDSP Station Code): Little York (LK) Load/Load Transformer Name: TR3 PTI BUS number: 45995 Voltage in kV (Transmission Level): 138kV Node (associated w/ load/load XFMR in NMMS): TR3 | Harris | HOUSTON | 2026-11-12 | OTH | BA | 9.96 | COD | 2025-08-20 | Yes | 2026-06-05 | 2026-06-15
24INR0502 | Medina City BESS | 2026-06-03 | Regis Medina, LLC | Station Name (TDSP Station Code): MEDINA; Load/Load Transformer Name: L_MEDICI9_1Y; PTI BUS number: 7430; Voltage in kV (Transmission Level): 69kV Transformers: 3x 4000kVA 800VAC Δ - 12.47kVA Υ 12,000 MVA connected, Running load limited to 9.99 MW | Bandera | SOUTH | 2026-11-26 | OTH | BA | 9.99 |  | 2023-01-18 | Yes | 2026-07-16 | 2026-07-29
24INR0602 | CPS Rio Nogales CT301 Rotor Replacement | 2024-04-29 | CPS Energy | 5362 RIONOG 345kV | Guadalupe | SOUTH | 2026-08-07 | GAS | CC | 3.1 |  | 2023-11-10 | Yes |  | 2024-04-03
24INR0645 | COYOTE SPRINGS AGR1 | 2024-06-05 | HEN INFRASTRUCTURE, LLC 1 | Station Name: COYOTSPR Load Name: COYOTE_1 Bus#: 38113 Voltage: 138 kV DAC: COYOTSPR_LD8 COYOTSPR/COYOTE_1/38113/COYOTSPR_LD8 | Reeves | WEST | 2026-06-23 | OIL | OT | 9.95 |  | 2023-10-16 | Yes
24INR0646 | SADDLEBACK AGR1 | 2024-06-05 | HEN INFRASTRUCTURE, LLC 1 | SADLBACK/SADLBK_1/38058/SADLBACK_LD8 | Reeves | WEST | 2026-06-23 | OIL | OT | 9.95 |  | 2023-10-16 | Yes
24INR0712 | Byrd Ranch Repower | 2026-04-15 | Byrd Ranch Storage LLC | 39700 SWEENY 138kV | Brazoria | COASTAL | 2027-01-22 | OTH | BA | 5.5 |  | 2020-12-14 | No
25INR0601 | East Bernard BESS | 2026-09-02 | Regis East Bernard LLC | Station Name: East Bernard Station Code: EB ERCOT Load Name: TR2 ERCOT BUS #: 44190 Voltage (Transmission level kV): 138 Node associated with load XFMR: 8045 CNP 5-Digit Code: E_BERN Short Code: EB TR2 Feeder: EB-81 CNP XFMR #: EB TR2 | Wharton | SOUTH | 2026-11-04 | OTH | BA | 9.5 |  | 2024-04-29 | Yes
25INR0602 | Hockley BESS | 2027-01-06 | Regis Hockley LLC | 30.021619, -95.846315 Station Name (Station Code): Hockley (HK) LONG CODE: HOCKLY Short Code: HK TR5 ERCOT Bus Name: Hockley Feeder: HK-91 ERCOT Load Name: TR5 CNP XFMR #: HK TR5 ERCOT Bus #: 45880 Node: 0101 | Harris | HOUSTON | 2027-03-01 | OTH | BA | 9.99 |  | 2024-04-29 | Yes
25INR0604 | Pledger BESS | 2026-09-02 | Regis Pledger LLC | 29.188382, -95.911558 CNP Pledger Substation LONG Name: PLEDGER Short Name: PG ERCOT Bus #: 43120 ERCOT Load Name: TR2 Connectivity Node: TR2 | Matagorda | COASTAL | 2026-11-04 | OTH | BA | 9.5 |  | 2024-04-29 | Yes
25INR0665 | CPS Rio Nogales CT201 Rotor Replacement | 2025-04-02 | CPS Energy | 5362 RIONOG 345kV | Guadalupe | SOUTH | 2026-08-07 | GAS | CC | 3.1 |  | 2025-02-07 | Yes |  | 2025-04-02
25INR0711 | Coyanosa Gas | 2025-10-27 | RPC Merchant, LLC | Station Name: COYANOSA Load Name: COYAN_2 TNMP Transformer Name: Xfmr T-2 (25kV) Bus#: 38380 Transmission Voltage: 138kV Node: 0033 | Winkler | WEST | 2026-12-17 | GAS | IC | 9.9 |  | 2025-03-13 | Yes
25INR0741 | Hollywood Solar Repower | 2025-12-17 | RED TAILED HAWK SOLAR LLC | 44060 BLU 345kV | Wharton | SOUTH | 2026-09-30 | SOL | PV | 9.9 |  | 2025-10-21 | Yes
26INR0734 | Alamo Street BESS2 | 2026-12-02 | Momentum Pilsner, LLC | TSP Station Name: Alamo Street Sub TNP TSP Station Code: ALAMO_ST Load Name / Load Transformer Name: ALAMO_2 Bus #: PTI Bus Number: 38331 Voltage (Transmission level kV): 138 Node (associated w/ load/load XFMR in NMMS): 9631 | Pecos | WEST | 2027-03-30 | OTH | BA | 9.99 |  | 2023-02-01 | Yes
26INR0773 | Seaway BESS | 2026-12-02 | Mount Whitney Energy Storage LLC | TSP Substation Name - Seaway TSP Substation Code - Seaway Load Name/Load Transformer Name - LOAD_T-4 Bus # / PTI Bus Number: 57670 Voltage (Transmission level Kv) - 138kV Node (associated w/ load/load XFMR in NMMS) - 0009 | Waller | HOUSTON | 2027-02-22 | OTH | BA | 9.9 |  | 2024-12-11 | Yes
26INR0774 | Wallis BESS2 | 2026-12-02 | Denali Energy Storage LLC | TSP Substation Name - Wallis TSP Substation Code - WA Load Name/Load Transformer Name - TR4 Bus # / PTI Bus Number: 44740 Voltage (Transmission level kV) - 138 kV Node (associated w/ load/load XFMR in NMMS) - TR4 | Austin | SOUTH | 2027-02-22 | OTH | BA | 9.9 |  | 2024-12-11 | Yes

## GIM Trends
GIM Trends
Reflects all Large Generator projects for which a Security Screening Study has been requested. The third table reflects all Small Generator projects whose GIM applications have been approved.
Excludes projects that have a status of Inactive (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects |  |  | Project Count | [5 empty] | Project Capacity (MW)
[6 empty] | GIM milestones | [5 empty] | Fuel Type
|  |  |  | Small Generator Not Model Ready | Small Generator Model Ready | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2023 | Sep | 1580 | 40 | 32 | 43 | 102 | 924 | 93 | 346 | 15 | 31639.72 | 141315.27 | 11383.73 | 0 | 0 | 53 | 114563.15 | 2235.03
| 2023 | Oct | 1628 | 41 | 32 | 49 | 102 | 952 | 99 | 353 | 16 | 31915.72 | 143221.48 | 13637.63 | 0 | 0 | 53 | 120534.12 | 2235.03
| 2023 | Nov | 1656 | 44 | 30 | 55 | 99 | 961 | 92 | 375 | 10 | 32509.57 | 142605.97 | 15457.28 | 0 | 0 | 53 | 124941.16 | 2385.03
| 2023 | Dec | 1671 | 41 | 28 | 39 | 116 | 974 | 92 | 381 | 12 | 34590.95 | 145654.02 | 15482.78 | 0 | 0 | 53 | 127067.73 | 2367
| 2024 | Jan | 1731 | 42 | 29 | 35 | 133 | 1011 | 95 | 386 | 12 | 36260.89 | 148135.32 | 15546.14 | 0 | 0 | 53 | 133592.45 | 2246.85
| 2024 | Feb | 1783 | 43 | 27 | 65 | 132 | 1023 | 102 | 391 | 13 | 37214.97 | 152097.86 | 16022.14 | 0 | 0 | 0 | 140219.15 | 2966.85
| 2024 | Mar | 1775 | 39 | 29 | 80 | 100 | 1035 | 101 | 391 | 64 | 35119.62 | 155272.52 | 15428.85 | 0 | 0 | 0 | 141483.67 | 2331.85
| 2024 | Apr | 1780 | 42 | 33 | 58 | 115 | 1025 | 112 | 395 | 15 | 32956.29 | 152916.51 | 15572.93 | 0 | 0 | 0 | 145000.4 | 2331.85
| 2024 | May | 1813 | 39 | 41 | 48 | 129 | 1023 | 125 | 408 | 9 | 33886.77 | 154225.29 | 15937.93 | 0 | 0 | 0 | 149001.55 | 2331.85
| 2024 | Jun | 1812 | 34 | 44 | 20 | 137 | 1023 | 140 | 414 | 27 | 31452.23 | 152433.39 | 17088.71 | 0 | 0 | 0 | 147743.45 | 2331.85
| 2024 | Jul | 1858 | 31 | 46 | 27 | 136 | 1033 | 158 | 427 | 5 | 33731.45 | 154407.17 | 22159.93 | 0 | 0 | 0 | 151810.97 | 2561.85
| 2024 | Aug | 1886 | 27 | 49 | 24 | 140 | 1057 | 152 | 437 | 8 | 33853.45 | 154770.45 | 25327.99 | 0 | 0 | 0 | 154799.02 | 2561.85
| 2024 | Sep | 1881 | 29 | 48 | 21 | 140 | 1050 | 158 | 435 | 19 | 34838.55 | 153658.25 | 25966.99 | 0 | 0 | 0 | 154264.31 | 2960.85
| 2024 | Oct | 1872 | 35 | 44 | 28 | 127 | 1039 | 159 | 440 | 29 | 33467.14 | 154860.41 | 25953.73 | 0 | 0 | 0 | 152579.89 | 3712.85
| 2024 | Nov | 1903 | 33 | 48 | 21 | 126 | 1070 | 156 | 449 | 11 | 35307.35 | 155675.7 | 27159.53 | 0 | 0 | 0 | 156529.81 | 3113.15

## data_GIM Trends_1
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Sep-25 | 532 | 117 | 1196 | 94 | 20 | 431.1647
Oct-25 | 530 | 116 | 1164 | 94 | 11 | 431.2039
Nov-25 | 528 | 122 | 1159 | 91 | 9 | 434.4146
Dec-25 | 539 | 121 | 1150 | 90 | 5 | 440.2987
Jan-26 | 574 | 121 | 1136 | 79 | 17 | 449.5541
Feb-26 | 576 | 122 | 1134 | 78 | 25 | 452.8891
Mar-26 | 583 | 128 | 1135 | 77 | 19 | 457.5034
Apr-26 | 578 | 116 | 1115 | 85 | 9 | 452.6039
May-26 | 569 | 113 | 1120 | 89 | 4 | 457.707
Jun-26 | 569 | 115 | 1109 | 85 | 4 | 462.1715
Jul-26 | 563 | 112 | 1122 | 41 | 5 | 456.0041
Aug-26 | 580 | 106 | 1092 | 41 | 4 | 453.8673
Sep-26 | 589 | 110 | 1059 | 41 | 8 | 453.1668

## data_GIM Trends_2
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Sep-25 | 43.6952 | 0.6 | 0 | 46.0934 | 159.9318 | 0 | 178.0528 | 3.5625 | 2042 | 25
Oct-25 | 47.8484 | 0.6 | 0 | 46.4223 | 158.1506 | 0 | 175.5791 | 3.3845 | 1999 | 51
Nov-25 | 52.6559 | 0.6 | 0 | 44.7857 | 159.537 | 0 | 174.369 | 3.2579 | 1994 | 13
Dec-25 | 53.7161 | 0.6 | 0 | 46.1909 | 161.8072 | 0 | 175.459 | 3.2579 | 1984 | 17
Jan-26 | 57.4034 | 0.6 | 0 | 47.9609 | 162.0668 | 0 | 178.7028 | 3.5725 | 2008 | 20
Feb-26 | 60.7149 | 0.6 | 0 | 47.793 | 162.9267 | 0 | 177.6419 | 3.8853 | 2008 | 21
Mar-26 | 63.8999 | 0.6 | 0 | 48.0888 | 165.2514 | 0 | 176.745 | 3.5713 | 2013 | 15
Apr-26 | 64.7456 | 1.9365 | 0 | 48.3492 | 163.4791 | 0 | 171.1058 | 3.5513 | 1965 | 43
May-26 | 70.6787 | 1.9365 | 0 | 48.2747 | 163.0914 | 0 | 171.5668 | 2.7525 | 1960 | 13
Jun-26 | 77.6066 | 1.9365 | 0 | 47.9906 | 161.5541 | 0 | 170.945 | 2.7525 | 1949 | 22
Jul-26 | 80.1801 | 1.9365 | 0 | 48.7817 | 157.9526 | 0 | 165.7341 | 1.9935 | 1906 | 56
Aug-26 | 81.704 | 1.9365 | 0 | 48.1308 | 156.2894 | 0 | 164.417 | 1.9935 | 1890 | 21
Sep-26 | 81.0339 | 3.2565 | 0 | 49.746 | 155.1229 | 0 | 162.5796 | 2.0435 | 1874 | 26

## data_GIM Trends_3
| # Not Model Ready | # Model Ready | MW Capacity
Sep-25 | 29 | 54 | 770.99
Oct-25 | 28 | 56 | 780.98
Nov-25 | 28 | 57 | 790.97
Dec-25 | 25 | 54 | 732.45
Jan-26 | 31 | 50 | 752.12
Feb-26 | 31 | 42 | 672.74
Mar-26 | 28 | 43 | 653.03
Apr-26 | 26 | 36 | 563.57
May-26 | 28 | 37 | 593.55
Jun-26 | 32 | 35 | 613.76
Jul-26 | 33 | 30 | 574.29
Aug-26 | 35 | 32 | 603.87
Sep-26 | 36 | 31 | 615.62

## data_GIM Trends_4
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2025 |  |  | 0.1002 | 0.00996
| 2026 |  | 0.5427 | 1.564 | 0.57959
| 2027 | 1.8474 | 0.20233 | 4.2964 | 4.2001 | 1.3865
| 2028 | 0.4699 | 0.1992 | 3.7313 | 6.4077 | 0.07963
| 2029 | 0.55611 | 1.0051 | 2.3173 | 3.669
| 2030 | 0.68108 | 2.8714 | 0.6036 | 0.25624
HOUSTON | 2025 | 0.014 |  |  |  | 0.05
| 2026 | 0.03 |  |  | 1.6126
| 2027 | 0.0354 |  | 0.05042 | 4.0045
| 2028 | 1.142 |  |  | 2.766 | 0.05
| 2029 |  |  | 0.35806 | 2.5315
| 2030 | 1.471 | 1.0294 |  | 0.20305 |  | 1.298 | 2.769
WEST | 2023 |  | 0.0072
| 2024 |  | 0.0103
| 2025 |  | 0.0224 | 0.16848 | 0.20246
| 2026 | 0.01989 | 1.9505 | 2.3304 | 1.5844 | 0.0199
| 2027 | 3.6342 | 3.2869 | 9.9406 | 6.7154
| 2028 | 6.184 | 6.0725 | 15.6269 | 14.6954 | 0.18
| 2029 | 1.1658 | 4.96 | 24.287 | 13.6888 | 0.732
| 2030 | 9.0002 | 7.6913 | 11.3035 | 3.4285
| 2031 | 1.3367 |  | 0.5028
| 2032 | 2.0511
NORTH | 2025 |  | 0.016 | 0.31573 |  | 0.1
| 2026 | 0.021 | 1.5156 | 4.7013 | 1.3455
| 2027 | 1.7246 | 0.56652 | 9.2134 | 9.3
| 2028 | 3.0036 | 1.3256 | 10.9607 | 18.9858 | 0.15 | 0.166 | 3.1696
| 2029 | 6.3367 | 0.1987 | 8.0993 | 14.7638
| 2030 | 6.2562 |  | 0.57141 | 2.3378 | 1.232
| 2031 | 2.5358

## Commissioning Update
Commissioning Approvals during September 2026
Commissioning Category | INR | Size Category | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 22INR0363 | Large | Hayhurst Texas Solar | Solar | Culberson | 2026-09-16 | 24.76
Commercial Operation Approved by ERCOT* | 20INR0091 | Large | Fagus Solar Park 1 SLF | Solar | Childress | 2026-09-11 | 166.42
Commercial Operation Approved by ERCOT* | 23INR0501 | Large | Soda Lake BESS 1 | Battery Storage | Crane | 2026-09-04 | 203.87
Commercial Operation Approved by ERCOT* | 21INR0469 | Large | Big Star Storage | Battery Storage | Bastrop | 2026-09-25 | 80
Commercial Operation Approved by ERCOT* | 21INR0413 | Large | Big Star Solar | Solar | Bastrop | 2026-09-25 | 203.1
Commercial Operation Approved by ERCOT* | 24INR0302 | Large | Pintail Pass BESS | Battery Storage | San Patricio | 2026-09-01 | 207.25
Commercial Operation Approved by ERCOT* | 26INR0736 | Small | Hovey Solar 2 | Solar | Pecos | 2026-09-22 | 8.05
Commercial Operation Approved by ERCOT* | 25INR0055 | Large | Three W Solar | Solar | Hill | 2026-09-23 | 110.89
Commercial Operation Approved by ERCOT* | 25INR0706 | Large | Bocanova Power II | Battery Storage | Brazoria | 2026-09-17 | 150.46
Commercial Operation Approved by ERCOT* | 25INR0672 | Large | Fagus Solar Park 2 SLF | Solar | Childress | 2026-09-11 | 166.57
Commercial Operation Approved by ERCOT* | 26INR0333 | Large | VERTUS ENERGY STORAGE | Battery Storage | Galveston | 2026-09-28 | 207.3
Commercial Operation Approved by ERCOT* | 25INR0766 | Small | Mesquite BESS2 | Battery Storage | Cameron | 2026-09-02 | 9.99
Synchronization Approved by ERCOT | 24INR0491 | Large | Gunnar BESS | Battery Storage | Hidalgo | 2026-09-08 | 154.75
Synchronization Approved by ERCOT | 20INR0236 | Large | New Hickory Solar | Solar | Jackson | 2026-09-15 | 209.15
Synchronization Approved by ERCOT | 24INR0313 | Large | Backbone Creek BESS | Battery Storage | Burnet | 2026-09-21 | 124.1
Synchronization Approved by ERCOT | 26INR0698 | Small | Staghorn Gas | Gas | Ward | 2026-09-18 | 9.99
Synchronization Approved by ERCOT | 23INR0249 | Large | Limewood Solar | Solar | Bell | 2026-09-15 | 204.6
Energization Approved by ERCOT | 26INR0702 | Small | Bexar Martinez BESS | Battery Storage | Bexar | 2026-09-15 | 9.99
Energization Approved by ERCOT | 21INR0362 | Large | Oystercatcher Solar | Solar | Ellis | 2026-09-02 | 198.43
Energization Approved by ERCOT | 24INR0313 | Large | Backbone Creek BESS | Battery Storage | Burnet | 2026-09-04 | 124.1
Energization Approved by ERCOT | 21INR0334 | Large | Nightfall Solar | Solar | Uvalde | 2026-09-22 | 180.87
Energization Approved by ERCOT | 21INR0253 | Large | Ulysses Solar | Solar | Coke | 2026-09-18 | 151.2

## Inactive Projects
Inactive Projects as of end of September 2026*
INR | Size Category | Project Name | Fuel | County | Inactive Date | MW **
13INR0010a | Large | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
20INR0025 | Large | Spinel Solar | Solar | Medina | 2019-09-10 14:02 | 30
20INR0024 | Large | Fluorite Solar | Solar | Uvalde | 2019-09-11 13:32 | 25
17INR0036 | Large | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
20INR0096 | Large | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200
19INR0031 | Large | Bestla Solar | Solar | Winkler | 2020-03-04 16:50 | 180
20INR0023 | Large | Agate Solar | Solar | Ellis | 2020-05-22 15:12 | 60
19INR0101 | Large | Tehuacana Wind | Wind | Limestone | 2020-05-28 10:23 | 600
21INR0503 | Large | Celeste Energy Storage | Battery Storage | Pecos | 2020-06-03 10:35 | 60.89
20INR0299 | Large | Sparkl BESS | Battery Storage | Guadalupe | 2020-09-16 12:30 | 20
19INR0161 | Large | Pierce Wind | Wind | Wharton | 2021-03-16 10:13 | 300
20INR0267 | Large | Greens Bayou Expansion | Gas | Harris | 2021-04-17 01:08 | 140
18INR0072 | Large | Blue Summit repower | Wind | Wilbarger | 2021-04-28 15:42 | 9.9
20INR0013 | Large | Basalt Solar | Solar | Uvalde | 2021-08-16 09:22 | 20
23INR0152 | Large | Madrone Energy Storage | Battery Storage | Comal | 2021-08-20 09:03 | 102.49
22INR0548 | Large | Fighting Jays Battery | Battery Storage | Fort Bend | 2022-02-25 17:43 | 53.2
19INR0099b | Large | Kontiki 2 Wind (ERNEST) | Wind | Glasscock | 2022-03-10 15:42 | 250.1
19INR0099a | Large | Kontiki 1 Wind (ERIK) | Wind | Glasscock | 2022-03-10 15:46 | 250.1
19INR0017 | Large | Tri-County Solar | Solar | Crane | 2022-09-21 15:00 | 177.75
16INR0033 | Large | Hart Wind (Old POI) | Wind | Castro | 2022-10-13 14:42 | 165
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during September 2026*
INR | Size Category | Project Name | Fuel | County | Cancel Date | MW **
24INR0459 | Large | Exodus BESS | Battery Storage | Caldwell | 2026-09-01 10:18 | 201.36
27INR0272 | Large | EMPower Odessa (TEF - Due Diligence) | Gas | Ector | 2026-09-03 | 122.8
29INR0162 | Large | Wolf Bone North Energy Center (OLD) | Gas | Reeves | 2026-09-04 14:38 | 1204
20INR0029 | Large | Lutum Wind | Wind | Clay | 2026-09-14 | 241.5
23INR0204 | Large | GALVANIC BESS | Battery Storage | Kinney | 2026-09-14 14:31 | 100
24INR0121 | Large | PHOTO BESS 1 | Battery Storage | Uvalde | 2026-09-14 14:32 | 75
24INR0122 | Large | PHOTO BESS 2 | Battery Storage | Uvalde | 2026-09-14 14:32 | 150
24INR0380 | Large | Photo BESS 3 | Battery Storage | Uvalde | 2026-09-14 14:33 | 100
23INR0206 | Large | PEREGRINE BESS | Battery Storage | Goliad | 2026-09-14 14:33 | 150
25INR0078 | Large | Peregrine BESS 2 | Battery Storage | Goliad | 2026-09-14 14:33 | 150
25INR0194 | Large | Photo Solar 1 | Solar | Uvalde | 2026-09-14 14:34 | 150
25INR0195 | Large | Photo Solar 2 | Solar | Uvalde | 2026-09-14 14:34 | 300
23INR0205 | Large | SUNSETTER BESS | Battery Storage | Uvalde | 2026-09-14 16:27 | 100
21INR0380 | Large | Charolais Solar | Solar | Matagorda | 2026-09-14 16:27 | 261.63
23INR0168 | Large | Charolais Storage | Battery Storage | Matagorda | 2026-09-14 16:28 | 150
22INR0266 | Large | Creekfield Solar | Solar | Fort Bend | 2026-09-14 16:28 | 161.34
22INR0379 | Large | Creekfield Storage | Battery Storage | Fort Bend | 2026-09-14 16:28 | 69
21INR0349 | Large | Pearl Crescent Solar | Solar | Colorado | 2026-09-14 16:28 | 208.35
21INR0470 | Large | Pearl Crescent Storage | Battery Storage | Colorado | 2026-09-14 16:28 | 50.26
22INR0244 | Large | Razorbill Solar | Solar | Matagorda | 2026-09-14 16:29 | 240
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.