## Contents
GINR Activity: Mar 01, 2020 to Mar 31, 2020
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GINR phase and fuel type
Project Details | A table that lists project details; only includes projects for which a Full Interconnection Study has been requested
GINR Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Apr 1, 2020 9:07:00 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online GINR system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
http://www.ercot.com/services/rq/re/reg/Resource%20Interconnection%20Handbook.pdf

## Acronyms
Acronyms
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle

## Summary
Summary |  |  | Major GINR Milestone Status by Fuel/Technology Type, MW
Currently tracking 620 generation interconnection or change requests as of Mar 31, 2020 |  |  | Includes only those projects for which a Screening Study (SS) has been requested and are not Inactive.
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Completed | SS Completed | TOTAL
Includes only those projects for which a Screening Study (SS) has been requested |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Started | FIS Completed
and are not Inactive |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA
Status of SS, FIS, and IA | Project Count | % of Total | Gas | Combined-Cycle |  | 697 |  | 103.3 | 83 | 45 | 292 | 1220.3
SS Started, FIS Not Started, No IA | 35 | 0.056361 | Gas | Combustion Turbine | 450 |  |  | 2298.7 | 418.6 | 140 | 837 | 4144.3
SS Started, FIS Started, No IA | 11 | 0.017713 | Gas | Internal Combustion Engine
SS Completed, FIS Not Started, No IA | 101 | 0.16264 | Gas | Compressed Air Energy Storage |  |  | 324.4 |  |  |  |  | 324.4
SS Completed, FIS Started, No IA | 309 | 0.49758 | Gas | Steam Turbine |  |  |  | 60 |  |  |  | 60
SS Completed, FIS Completed, No IA | 21 | 0.033816 | Gas | Fuel Cell
SS Completed, FIS Started, IA | 45 | 0.072464 | Gas | Total gas | 450 | 697 | 324.4 | 2462 | 501.6 | 185 | 1129 | 5749
SS Completed, FIS Completed, IA | 99 | 0.15942 | Coal |  |  | 493 | [5 empty] | 493
Total Interconnection Requests | 621 |  | Wind |  | 914 | 34 | 1308 | 13092.59 | 640.2 | 4612.12 | 8287.49 | 28888.4
Inactive (since last month) | 7 |  | Solar |  | 5466.28 | 1438.05 | 14762.71 | 40771.28 | 1925.67 | 4931.49 | 6942.69 | 76238.17
Cancelled (since last month) | 21 |  | Biomass
| Capacity, MW |  | Other | Battery | 980.2 | 311.46 | 3560.2 | 5037 | 50 | 242.22 | 200 | 10381.08
Total Capacity Under Study | 122112.65 |  | Other* |  |  | 50 | 150 | 150 | 13 |  |  | 363
Interconnection Agreements Executed | 26530.01 |  | TOTAL |  | 7810.48 | 3024 | 20105.31 | 61512.87 | 3130.47 | 9970.83 | 16559.18 | 122113
Inactive (since last month) | 1574
Cancelled (since last month) | 3809.32
* Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.

## Project Details
GINR Project Details
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GINR system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
Project Attributes | [10 empty] | Changes from Last Report | GINR Project Milestone Dates
INR | Project Name | GINR Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
11INR0062 | Shaffer | SS Completed, FIS Completed, IA | Clearway Energy | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2020-04-24 | WIN | WT | 226 | COD | 2009-04-23 | 2009-06-16 | 2009-07-21 | 2018-06-13 | 2013-07-02 | Yes | Not Required | Not Required | Not Required | 2018-04-18 | 2018-09-28 | 2018-07-31 |  |  | 2019-03-27 | 2019-04-05
12INR0060 | Wilson Ranch | SS Completed, FIS Completed, IA | ENGIE | 76003 Big Hill 345kV | Schleicher | WEST | 2020-03-31 | WIN | WT | 199.5 | COD | 2010-12-03 | 2014-03-21 | 2011-06-06 | 2018-05-31 | 2018-05-21 | Yes | Not Required | Not Required | Not Required | 2018-05-21 | 2018-09-28 | 2018-04-30 |  |  | 2018-10-11 | 2018-11-29
14INR0009 | WKN Amadeus Wind | SS Completed, FIS Completed, IA | WKN | tap 345kV 11305 Dermott - 60706 Kirchhoff | Fisher | WEST | 2020-10-30 | WIN | WT | 250.12 |  | 2011-01-24 | 2011-03-18 | 2011-09-12 | 2019-11-01 | 2018-03-15 | Yes | Not Required | Not Required | Not Required | 2019-03-07 | 2019-10-28 | 2019-11-01
14INR0033 | Goodnight Wind | SS Completed, FIS Started, IA | FGE Power | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2021-12-30 | WIN | WT | 504.4 | COD | 2012-07-24 | 2012-09-19 | 2013-03-04 |  | 2018-03-07 | No | Not Required | Not Required | Not Required
15INR0034 | El Algodon Alto W | SS Completed, FIS Started, No IA | Eon | tap 345kV 8455 Lon Hill -8606 Goddard | San Patricio | COASTAL | 2021-12-15 | WIN | WT | 201 | Status Change INA-to-PLN | 2013-02-04 | 2013-03-25 | 2013-08-16 |  |  | No | Not Required | Not Required | Not Required
15INR0044 | Corazon Solar | SS Completed, FIS Started, IA | Corazon Energy, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2021-05-31 | SOL | PV | 200 |  | 2013-09-06 | 2013-09-16 | 2013-08-20 |  | 2020-01-09 | No | Not Required | Not Required | Not Required
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2020-05-26 | WIN | WT | 162.1 | COD | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10
16INR0054 | NA | SS Completed, FIS Completed, IA | NASA | 42970 Nasa 138kV | Harris | HOUSTON | 2018-09-01 | GAS | CC | 12 |  | 2015-03-10 | 2015-04-01 | 2015-03-10 | 2016-01-26 | 2016-10-27 | Yes | Not Required | Not Required |  | 2016-11-10 | 2018-09-28 |  |  |  |  | 2017-11-27
16INR0076 | Hudson (Ineos/Brazoria) | SS Completed, FIS Completed, IA | Ineos | 42100 Hudson 138kV | Brazoria | COASTAL | 2020-04-30 | GAS | GT | 96 | COD | 2015-01-12 | 2015-03-19 | 2015-06-24 | 2017-08-24 | 2017-12-05 | Yes | 2017-02-10 | 2017-02-10 | 2018-01-10 | 2018-10-09 | 2019-02-12 | 2018-08-01 |  |  | 2019-02-12 | 2019-08-16
16INR0085 | Priddy Wind | SS Completed, FIS Started, No IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2021-09-01 | WIN | WT | 300 |  | 2015-01-14 | 2015-02-10 | 2015-03-06 |  |  | No | Not Required | Not Required | Not Required
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, No IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2020-04-30 | WIN | WT | 3 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 |  | No | Not Required | Not Required | Not Required
18INR0076 | Wolf Hollow 2 repower | SS Completed, FIS Started, No IA | Exelon | 1877 Mitchell Bend 345kV | Hood | NORTH | 2020-06-01 | GAS | CC | 44 |  | 2018-04-24 | 2018-04-24 | 2018-04-24 |  |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-19
19INR0176 | Roughneck Storage | SS Completed, FIS Completed, No IA | Glidepath | 43380 W Columbia 138kV | Brazoria | COASTAL | 2021-07-01 | OTH | BA | 50 |  | 2018-05-09 | 2018-07-13 | 2018-11-07 | 2019-11-04 |  | No | Not Required | Not Required | Not Required
20INR0287 | STP Unit 1 repower | SS Completed, FIS Completed, No IA | South Texas Electric Generating Station Unit 1 | 5915 STP 345kV | Matagorda | COASTAL | 2020-04-30 | NUC | ST | 13 |  | 2019-07-25 | 2019-10-22 | 2019-09-17 | 2019-10-28 |  | Yes | Not Required | Not Required |  | 2019-10-28 | 2019-10-28 | 2019-10-28
20INR0301 | Colorado Bend Power I LLC (Repower) | SS Started, FIS Started, No IA | Colorado Bend Power I, LLC | Dyann Substation (3821 S SH 60 Hwy, City of Wharton, Wharton County, TX 77488 | Wharton | SOUTH | 2020-07-07 | GAS | CC | 0 |  | 2020-03-06 |  | 2020-02-28 |  |  | No
20INR0308 | Gibbons Creek TEERP | SS Started, FIS Started, No IA | TEERP Power Station LLC | 967 Gibbons Creek 345kV | Grimes | NORTH | 2020-07-27 | COAL | ST | 493 | FIS Request |  |  | 2020-03-29 |  |  | No | 2011-05-31 | Not Required | 2020-03-29
21INR0012 | Air Products | SS Completed, FIS Started, No IA | Air Products | 39140 TNTxCityMain 69kV | Galveston | HOUSTON | 2021-05-15 | GAS | ST | 0 |  | 2018-06-07 | 2018-08-01 |  |  |  | No
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2026-04-30 | OTH | OT | 50 |  | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  | No | Not Required | Not Required

## GINR Trends
GINR Trends
Reflects all projects for which a Security Screening Study has been requested.
Excludes projects that have a status of Suspended (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects | Project Count | [5 empty] | Project Capacity (MW)
|  |  |  | GINR milestones | [5 empty] | Fuel Type
|  |  |  | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2017 | Mar | 264 | 11 | 27 | 131 | 3 | 92 | 3 | 26593 | 15338 | 16750 | 0 | 240 | 0 | 0 | 0
| 2017 | Apr | 284 | 28 | 28 | 136 | 3 | 89 | 5 | 28470 | 17054 | 19316 | 0 | 240 | 0 | 0 | 0
| 2017 | May | 287 | 23 | 35 | 139 | 3 | 87 | 4 | 28259 | 18012 | 17620 | 0 | 240 | 0 | 0 | 0
| 2017 | Jun | 320 | 33 | 45 | 154 | 3 | 85 | 4 | 31835 | 22275 | 15656 | 0 | 240 | 0 | 30 | 0
| 2017 | Jul | 323 | 38 | 44 | 155 | 3 | 83 | 7 | 30279 | 21974 | 15656 | 0 | 0 | 0 | 30 | 0
| 2017 | Aug | 333 | 32 | 61 | 155 | 5 | 80 | 11 | 30068 | 23814 | 14357 | 0 | 0 | 0 | 0 | 0
| 2017 | Sep | 336 | 35 | 60 | 157 | 5 | 79 | 18 | 29915 | 24089 | 12001 | 0 | 0 | 0 | 0 | 0
| 2017 | Oct | 339 | 25 | 66 | 163 | 9 | 76 | 6 | 30090 | 24729 | 14201 | 0 | 0 | 0 | 0 | 0
| 2017 | Nov | 340 | 14 | 64 | 172 | 15 | 75 | 17 | 29882 | 24893 | 13747 | 0 | 0 | 0 | 0 | 0
| 2017 | Dec | 337 | 7 | 57 | 166 | 19 | 73 | 8 | 30198 | 24123 | 13969 | 0 | 0 | 0 | 30 | 0
| 2018 | Jan | 335 | 15 | 56 | 169 | 21 | 74 | 17 | 31420 | 22739 | 12768 | 0 | 0 | 0 | 0 | 0
| 2018 | Feb | 334 | 11 | 46 | 177 | 27 | 73 | 9 | 32258 | 22413 | 12727 | 0 | 0 | 0 | 0 | 0
| 2018 | Mar | 340 | 14 | 41 | 179 | 27 | 79 | 8 | 32897 | 23515 | 12065 | 0 | 0 | 0 | 0 | 0
| 2018 | Apr | 349 | 18 | 48 | 172 | 30 | 81 | 4 | 33427 | 24709 | 13484 | 0 | 0 | 0 | 0 | 0
| 2018 | May | 369 | 33 | 36 | 180 | 34 | 86 | 13 | 33799 | 27766 | 13442 | 0 | 0 | 0 | 200 | 0

## data_GINR Trends_1
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Mar-19 | 115 | 33 | 247 | 68 | 42 | 100.8368
Apr-19 | 120 | 30 | 260 | 79 | 38 | 103.9696
May-19 | 130 | 26 | 279 | 68 | 60 | 108.4708
Jun-19 | 135 | 27 | 285 | 68 | 53 | 108.8963
Jul-19 | 143 | 25 | 295 | 87 | 36 | 111.9705
Aug-19 | 132 | 27 | 303 | 91 | 30 | 112.6154
Sep-19 | 130 | 26 | 298 | 91 | 30 | 111.0678
Oct-19 | 135 | 29 | 294 | 88 | 36 | 109.9089
Nov-19 | 133 | 29 | 300 | 89 | 38 | 110.3922
Dec-19 | 129 | 21 | 325 | 78 | 31 | 112.1498
Jan-20 | 132 | 23 | 333 | 78 | 47 | 119.3547
Feb-20 | 137 | 27 | 334 | 87 | 48 | 124.0624
Mar-20 | 144 | 21 | 320 | 101 | 35 | 122.1127

## data_GINR Trends_2
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Mar-19 | 10.5366 | 0 | 0.045 | 35.5553 | 50.9999 | 0 | 3.2652 | 0.4418 | 505 | 18
Apr-19 | 10.1026 | 0 | 0.045 | 35.6443 | 54.6555 | 0 | 3.5012 | 0.3 | 527 | 9
May-19 | 9.7366 | 0 | 0.045 | 35.6894 | 58.5795 | 0 | 4.1204 | 0.3 | 563 | 11
Jun-19 | 9.7396 | 0 | 0 | 35.7392 | 59.1607 | 0 | 3.9568 | 0.3 | 568 | 19
Jul-19 | 9.2826 | 0.013 | 0 | 36.0485 | 62.3561 | 0 | 3.9704 | 0.3 | 586 | 11
Aug-19 | 8.2068 | 0.013 | 0 | 35.2757 | 64.5795 | 0 | 4.1998 | 0.3406 | 583 | 12
Sep-19 | 7.4052 | 0.013 | 0 | 34.5535 | 64.3437 | 0 | 4.4524 | 0.3 | 575 | 15
Oct-19 | 7.4455 | 0.013 | 0 | 31.6832 | 64.7897 | 0 | 5.6274 | 0.35 | 582 | 16
Nov-19 | 5.898 | 0.013 | 0 | 32.2527 | 64.664 | 0 | 7.2144 | 0.35 | 589 | 11
Dec-19 | 5.607 | 0.013 | 0 | 30.174 | 67.8079 | 0 | 7.7903 | 0.35 | 584 | 19
Jan-20 | 5.607 | 0.013 | 0 | 30.5733 | 73.6368 | 0 | 8.9656 | 0.55896 | 613 | 3
Feb-20 | 5.507 | 0.013 | 0 | 30.5147 | 77.6991 | 0 | 9.9786 | 0.35 | 633 | 1
Mar-20 | 5.749 | 0.013 | 0.493 | 28.8884 | 76.2382 | 0 | 10.3811 | 0.35 | 621 | 21

## data_GINR Trends_3
|  | Gas | Coal | Wind | Solar | Battery | Other
COASTAL | 2020 | 0.336 |  | 1.8818 | 0.27 |  | 0.013
| 2021 | 0.117 |  | 1.2112 | 3.3601 | 1.095
| 2022 | 0.06 |  | 0.401 | 1.1842 | 0.2
| 2023 |  |  |  | 0.55
HOUSTON | 2018 | 0.012
| 2020 | 0.374
| 2021 | 1.9258 |  |  | 1.8465
| 2022 |  |  | 0.4 | 0.448
| 2023 | 0.697
| 2025 | [5 empty] | 0.05
| 2026 | [5 empty] | 0.05
WEST | 2019 |  |  | 0
| 2020 | 0.083 |  | 5.1689 | 3.501 | 0.15526
| 2021 |  |  | 7.1656 | 12.746 | 1.9434
| 2022 |  |  | 1.862 | 10.127 | 1.0208
| 2023 | 0.45 |  |  | 1.494 | 0.325
NORTH | 2020 | 0.065 | 0.493 | 0.47288 | 0.62655 | 0.11012
| 2021 | 0.8403 |  | 2.5492 | 8.9749 | 1.312
| 2022 |  |  | 0.451 | 6.8165 | 1.0783
| 2023 | 0.3244 |  |  | 1.4839
| 2024 |  |  |  | 0.40058 | 0.1001
| 2025 | [5 empty] | 0.1
| 2026 | [5 empty] | 0.15
PANHANDLE | 2020 |  |  | 0.6029 | 0.2408
| 2021 | 0.0815 |  | 0.8236 | 1.4618 | 0.1
| 2022 |  |  | 0.5662 | 1.6368
| 2023 |  |  |  | 0.68321
| 2024 |  |  |  | 0.345
SOUTH | 2020 | 0.064 |  | 0.83451 | 0.6218 | 0.0882

## Commissioning Update
Commissioning Approvals During March 2020
Commissioning Category | INR | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 18INR0067 | Gopher Creek Wind | Wind | Borden | 2020-03-09 | 158
Synchronization Approved by ERCOT | 20INR0272 | RIO NOGALES AGP UPGRADE CT3 | Gas | Guadalupe | 2020-03-09 | 19
Synchronization Approved by ERCOT | 19INR0014 | Formosa Increase | Gas | Calhoun | 2020-03-04 | 240
Energization Approved by ERCOT | 19INR0083 | Oberon Solar | Solar | Ector | 2020-03-04 | 180
Energization Approved by ERCOT | 18INR0075 | Gulf Wind 1 repower | Wind | Kenedy | 2020-03-31 | 0
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of March 2020*
INR | Project Name | Fuel | County | Inactive Date | MW **
20INR0025 | Spinel Solar | Solar | Medina | 2019-08-13 16:03 | 30
20INR0023 | Agate Solar | Solar | Ellis | 2019-08-13 16:05 | 60
20INR0024 | Fluorite Solar | Solar | Uvalde | 2019-08-19 18:20 | 25
16INR0044 | Halyard Wharton | Gas | Wharton | 2019-08-30 13:26 | 484
17INR0053 | HHGT repower Horse13+CallD | Wind | Taylor | 2019-08-30 13:32 | 44
13INR0025 | Northdraw Wind | Wind | Randall | 2019-08-30 13:38 | 150
16INR0014b | Cattleman Wind B | Wind | Castro | 2019-08-30 13:40 | 201.6
17INR0010 | FGE Texas 2 Gas | Gas | Mitchell | 2019-08-30 13:41 | 742.9
16INR0112 | Loma Pinta Wind | Wind | La Salle | 2019-08-30 13:44 | 200
16INR0014 | Cattleman Wind A | Wind | Castro | 2019-08-30 13:48 | 201.6
12INR0059b | HOVEY (Barilla Solar 1B) | Solar | Pecos | 2019-08-30 13:50 | 7.4
16INR0099 | Hecate Solar | Solar | Brewster | 2019-08-30 14:57 | 33
16INR0101 | Chatee Solar | Solar | Pecos | 2019-08-30 14:59 | 57
16INR0102 | Owego Solar | Solar | Pecos | 2019-08-30 15:01 | 74
17INR0043 | Vaquero 1 Wind | Wind | Zapata | 2019-08-30 15:02 | 400
13INR0010a | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
14INR0030c | Panhandle Wind 3 | Wind | Carson | 2019-09-24 09:41 | 248
20INR0021 | Garnet Solar | Solar | Williamson | 2019-10-01 08:30 | 20
19INR0055 | Monte Cristo 2 Wind | Wind | Hidalgo | 2019-10-24 18:00 | 236.9
19INR0133 | La Joya II Wind | Wind | Hidalgo | 2019-10-24 18:05 | 236.9
17INR0036 | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
20INR0096 | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200

## Cancellation Update
Projects Cancelled by the Developer during March 2020*
INR | Project Name | Fuel | County | Cancel Date | MW **
19INR0096 | Shamrock Wind | Wind | Crockett | 2020-03-03 14:31 | 201.6
19INR0172 | Dillon Gulch Wind | Wind | Nolan | 2020-03-13 18:42 | 175
21INR0252 | Monaville Solar | Solar | Waller | 2020-03-27 15:10 | 100
19INR0097 | Shamrock Wind II | Wind | Crockett | 2020-03-03 14:31 | 201.6
19INR0020b | SP-Pecos Bend Solar B | Solar | Pecos | 2020-03-11 16:33 | 180
19INR0020 | SP-Pecos Bend Solar A | Solar | Pecos | 2020-03-11 16:32 | 200
18INR0027 | Ponwar Solar Farm | Solar | Upton | 2020-03-12 14:38 | 180
19INR0098 | Pease River Wind | Wind | Hardeman | 2020-03-03 14:42 | 301.4
19INR0007 | Charbray Solar | Solar | Mitchell | 2020-03-12 14:38 | 200
19INR0028 | Normande Solar Farm | Solar | Borden | 2020-03-12 14:39 | 360
21INR0419 | Mockingbird Solar | Solar | Hill | 2020-03-20 09:22 | 200
19INR0147 | March Road Solar | Solar | Tom Green | 2020-03-04 10:57 | 200
21INR0397 | AltaRanch | Gas | Harris | 2020-03-03 08:56 | 300
20INR0295 | McAdoo repower | Wind | Dickens | 2020-03-02 16:41 | 14.72
19INR0138 | Buffalo Gap 4 | Wind | Nolan | 2020-03-13 18:41 | 175
21INR0464 | Old 300 Storage | Other | Fort Bend | 2020-03-20 15:50 | 50
20INR0150 | Robles Storage | Other | Dimmit | 2020-03-16 11:44 | 100
20INR0126 | Robles Solar | Solar | Dimmit | 2020-03-16 11:44 | 200
19INR0033 | Murphy Lake Solar | Solar | Kaufman | 2020-03-23 01:40 | 120
19INR0171 | Concho Valley Solar | Solar | Tom Green | 2020-03-02 08:17 | 150
* Includes only those projects cancelled after the developer makes a Full Interconnection Study (FIS) request.