## Project Details - Large Gen
GIM Project Details - Large Generators
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GIM system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
A “1-1-1900” date is used to signify that an actual date for a project milestone is not available. This typically occurs for project data migrated from the legacy GINR database to the RIOO system.
Project Attributes | [10 empty] | Changes from Last Report | GIM Project Milestone Dates
INR | Project Name | GIM Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | McCrae Wind Energy II, LLC | 59903 Bearkat 345kV | Glasscock | WEST | 2026-12-03 | WIN | WT | 162.1 |  |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
16INR0049 | Nazareth Solar | SS Completed, FIS Completed, IA | TX Nazareth Solar, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala C2 | Castro | PANHANDLE | 2027-08-31 | SOL | PV | 203 |  | 2014-07-07 | 2014-06-19 | 2014-07-25 | 2014-07-01 | 2025-07-29 | No | 2026-03-05 | Yes | Not Required | Not Required | Not Required | 2024-03-22
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2027-03-01 | WIN | WT | 201.6 | COD | 2014-12-30 | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | No | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
16INR0085 | Priddy Wind | SS Completed, FIS Completed, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2026-12-31 | WIN | WT | 302.4 |  | 2015-03-06 | 2015-01-14 | 2015-02-10 | 2015-03-06 | 2021-04-30 | No | 2020-08-13 | Yes | Not Required | Not Required | Not Required | 2021-03-29 | 2021-04-30 | 2021-04-30 |  |  | 2021-10-13 | 2021-11-19
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, IA | Big Sampson Wind Project, LLC | tap 345kV 76015 Cedar Canyon - 7053 Noelke | Crockett | WEST | 2026-09-01 | WIN | WT | 265.4 |  |  | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2024-10-30 | Yes | 2019-11-08 | Yes | Not Required | Not Required | Not Required | 2024-10-31 | 2024-11-04 | 2024-11-04 |  |  | 2025-06-04 | 2025-06-16
16INR0112 | Loma Pinta Wind | SS Completed, FIS Started, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2026-12-31 | WIN | WT | 197.01 |  |  | 2015-05-18 | 2015-07-02 | 2015-05-18 |  | No | 2017-12-13 | No | Not Required | Not Required | Not Required
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2026-08-28 | WIN | WT | 242.6 | COD |  | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | No | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31 |  |  | 2020-08-24 | 2020-11-25
17INR0043 | Vaquero 1 Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | SOUTH | 2027-01-15 | WIN | WT | 400 |  | 2016-04-01 | 2016-04-01 | 2016-05-10 | 2016-04-01 |  |  |  | No | Not Required | Not Required | Not Required
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2027-03-31 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | No | 2019-05-22 | Yes | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-03-16
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2027-03-31 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 | No | 2009-06-26 | No | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-09-10
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2026-06-30 | WIN | WT | 32 |  | 2017-03-09 | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | No | 2006-11-14 | No | Not Required | Not Required | Not Required | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-04
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | TRENT WIND FARM LLC | 1338 Eskota 138kV | Nolan | WEST | 2026-01-01 | WIN | WT | 6.4 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | No | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | DESERT SKY WIND FARM LLC | two LCRA 138kV | Pecos | WEST | 2023-05-16 | WIN | WT | 7.2 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | No | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0009 | Eagle Pines Gas | SS Completed, FIS Started, No IA | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | NORTH | 2028-10-30 | GAS | CC | 1173.5 |  | 2015-03-24 | 2015-03-30 | 2015-06-23 | 2015-04-29 |  |  |  | No | 2017-02-14 | 2015-11-04 |  |  |  |  | 2026-01-30 | 2028-08-14
18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2026-08-31 | WIN | WT | 182.4 |  | 2016-07-22 | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | No | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31 |  |  | 2021-01-08 | 2021-04-23
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2026-09-05 | WIN | WT | -7.2 |  | 2017-07-06 | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | No | 2018-10-16 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-23 | 2019-10-28 |  |  |  | 2020-07-28
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 9.3 |  | 2018-05-22 | 2018-05-22 | 2018-08-29 | 2018-05-22 | 2018-10-03 | No | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WIN | WT | 3 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 | No | 2002-10-23 | No | Not Required | Not Required | Not Required
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | No | 2018-12-12 | Yes | Not Required | Not Required | Not Required | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2019-11-07 | 2019-11-13
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | No | 2018-12-18 | Yes | Not Required | Not Required | Not Required | 2018-11-29 | 2018-11-29 | 2020-10-30 |  |  |  | 2018-12-19
19INR0002 | Grandfalls Solar | SS Completed, FIS Completed, IA | King Mountain Solar, LLC | 842 King Mountain Station 345kV | Upton | WEST | 2026-11-25 | SOL | PV | 175.6 |  | 2016-05-24 | 2016-05-24 | 2016-06-06 | 2016-05-24 | 2025-12-17 | No | 2025-01-23 | Yes | Not Required | Not Required | Not Required | 2026-01-08 | 2026-01-26 | 2026-01-26 |  |  | 2026-06-24 | 2026-07-15
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, IA | Monte Alto Windpower, LLC | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2028-12-31 | WIN | WT | 199.2 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2022-03-22 | Yes | Not Required | Not Required | Not Required | 2025-02-12
19INR0035 | Norton Solar | SS Completed, FIS Completed, IA | TAI Norton Solar, LLC | 60451 Garnet 138kV | Runnels | WEST | 2025-11-24 | SOL | PV | 128.48 |  | 2017-11-08 | 2017-03-06 | 2017-04-20 | 2017-11-08 | 2024-10-29 | No | 2019-06-20 | Yes | Not Required | Not Required | Not Required | 2019-07-12 | 2023-05-30 | 2025-01-16 |  |  | 2025-07-24 | 2025-08-06
19INR0041 | Myrtle Solar | SS Completed, FIS Completed, IA | Myrtle Solar, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2027-06-21 | SOL | PV | 321.2 |  |  | 2017-03-15 | 2017-04-28 | 2017-05-09 | 2022-01-25 |  | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2019-11-30 | 2020-05-06 | 2022-02-01 |  |  | 2022-12-07 | 2022-12-20